## Sheet1
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | JOB CLOUD
PROJECT SPONSOR | CLOUD COUNSELAGE Pvt LTD
PROJECT MANAGER | JAYANTH G S
EXPECTED START DATE | 2020-06-15
EXPECTED COMPLETION DATE | 2020-07-31
ESTIMATED COST | FREE
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE | TO FIND BEST SEGMENTATION MODEL ON A DATA SET USING DATA SCIENCE
BUSINESS CASE | company can recruite interns better next times for their internship program thereby improving product thereby improving business.
GOALS/METRICS | To classify model based on the requirements.
EXPECTED DELIVERABLES | Classified Model with great accuracy
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE | none
OUTSIDE OF SCOPE | none
PROJECT RESOURCES AND COSTS
PROJECT TEAM | Romil
SUPPORT RESOURCES | Dataset,Laptops,Internet
SPECIAL NEEDS
PROJECT BENEFITS AND CUSTOMERS
PROCESS OWNER | Romil Nisar
KEY STAKEHOLDERS | Jayanth G S, Nirbhey Singh Pahwa
END CUSTOMER | CLOUD COUNSELAGE
EXPECTED BENEFIT | Better recruitment next time which leads to better quality of interns.
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS | Technical risk:Unmet requirements-forgetting to include a single requirement can cost us time & budget overhead, or worse, poor website quality. Resource risk:Uncertainty in resource availability: Interns might go on leave on commencement of university exams. Due to the COVID-19 outbreak, the exact examination dates are not available.On team change over, new members needs to get trained and it's time-consuming.Also, the current team members lack knowledge in back-end development. This might result in the escalation of project completion.
ASSUMPTIONS | Job Cloud will help all the CC interns to get a job.
CONSTRAINTS | Very stringent time for the completion of the project.