## Sheet1
PROJECT PLAN FOR EXECUTION PHASE
PROJECT NAME | JOB CLOUD
PROJECT MANAGER | JAYANTH G S |  | EXECUTION PHASE START DATE: |  | 2020-06-17
PROJECT DELIVERABLE | JOB CLOUD CLASSIFIER |  | EXECUTION PHASE END DATE: |  | 2020-06-24
PROJECT SCOPE
PROJECT START DATE | 2020-06-15
PROJECT END DATE | 2020-07-31
OVERALL PROGRESS | DONE
PARENT FEATURE | FEATURES | REQUIRED TIME (IN HRS) | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem | 0 | 2020-06-15 | 2020-06-15 | 1 | COMPLETED
| 1.2 Create a project charter | 1 | 2020-06-25 | 2020-06-25 | 1 | COMPLETED
| 1.3 Requirement gathering | 1 | 2020-06-26 | 2020-06-26 | 1 | COMPLETED
2 Planning
| 2.1 Baseline project plan | 1 | 2020-06-16 | 2020-06-16 | 1 | COMPLETED
| 2.2 Plan the design,methods | 2 | 2020-06-17 | 2020-06-17 | 1 | COMPLETED
3 Execution
| 3.1 Finalize design | 1 | 2020-06-18 | 2020-06-18 | 1 | COMPLETED
| 3.2 Data Cleaning | 30 mins | 2020-06-19 | 2020-06-19 | 1 | COMPLETED
| 3.3 Preprocessing | 1 | 2020-06-20 | 2020-06-20 | 1 | COMPLETED
| 3.4 Data Visualization | 4 | 2020-06-21 | 2020-06-21 | 1 | COMPLETED
| 3.5 Model for classifier | 3 | 2020-06-22 | 2020-06-22 | 1 | COMPLETED
| 3.6 Accuracy Testing | 1 | 2020-06-23 | 2020-06-23 | 1 | COMPLETED
4 Closure |  | 2 | 2020-06-24 | 2020-07-28 | 1 | COMPLETED